## Sheet1
Bug Report of ScienceTribes.com
Date:08/08/07
Bug-id | Bug Description | module | Classification | Affected Function | Steps to Replicate | Assigned To | Assigned On | Status | REMARKS
1 | repetation of word "of" | http://www.sciencetribes.com/products.php |  |  | there is a repetation of word
[5 empty] | of' in the link page |  |  | FIXED
http://www.sciencetribes.com/products.php
at 2nd para 2nd line
[5 empty] | when we enter all the details in the profile page and |  |  | FIXED
2 | Save &Cancel buttons are | http://www.sciencetribes.com/mem_personal.php |  |  | and click the button 'save' it is not accepting and
| replaced with "PREV,NEXT, |  |  |  | prev','next' & 'skip now' buttons are shown,
| SKIP NOW" buttons,and also |  |  |  | here is the link,
| check for validations.it can be |  |  |  | http://www.sciencetribes.com/mem_personal.php
| seen in the scren shot no.4 |  |  |  | you can also observe it pictorialy in sceen shot slide
no.4, and also check for validations
3 | missing of ':' in the ADD | http://www.sciencetribes.com/forumsetup.php |  |  | In the ADD FORUM page, ":" (colon) is missing |  |  | FIXED
| FORUM page |  |  |  | it can be observed in screen shot slide no. 3
4 | Standardisation missing | http://www.sciencetribes.com/forum_details.php?crypt=Zm9ydW1pZD04OQ%3D%3D |  |  | Standardisation Missing in the Design Issue,it can be |  |  | FIXED
| there is a Design issue in the |  |  |  | seen in screen shot slide no.2
conformation step of
ADDFORUM
5 | Forgot password mail there | http://www.sciencetribes.com/pass_recover.php?key=x26c36tz |  |  | In the forgot Password module,the customer gets |  |  | FIXED
| is no space b/w |  |  |  | a mail from ADMIN ,regarding new Password it can be
| "sciencetribes.com & pass- |  |  |  | seen in the screen shot slide no. 1
word" words
6 | Colon (:) missing at "Folder | http://www.sciencetribes.com/documentfoldersetup.php |  |  | In the Information services header bar,go to the Document |  |  | FIXED
| name,Select a folder,Status" |  |  |  | services,in that go to ADD FOLDER option,you can
| fields in the ADD FOLDER |  |  |  | observe it in the screen shot slide no.5
service option
7 | colon(:) is missing at the | http://www.sciencetribes.com/documentsetup.php |  |  | In the Information Service header bar,go to the Document
| "Select a document setup, |  |  |  | service,in that go to ADD DOCUMENT option,you can
| select a folder,status,revision" |  |  |  | observe it in the screen shot slide no. 6 |  |  | FIXED
fields in the ADD DOCUMENT
service option.
8 | There is a design isue in the | http://www.sciencetribes.com/show.php?crypt=Y3JlYXRlX3Bvc3Rlcj0xJnBvc2lkPTYw |  |  | Go to the Information Service header bar,goto the |  |  | FIXED
| ADD POSTER service option of |  |  |  | ADD POSTER option and follow the flow in that at last
| the last step "Confirmation" |  |  |  | "confirmation" step you will find it,you can see it in the
| option, and there is also a |  |  |  | screen shot slide no. 8
loss of confirmation data
9 | colon (:) is missing at the | http://www.sciencetribes.com/createPoster.php |  |  | Go to the Information Service header bar,goto the |  |  | FIXED
| "select a poster,poster setup, |  |  |  | POSTER option and then goto the ADD POSTER
| status" fields in the ADD POSTER |  |  |  | option , it can be seen in the screen shot slide no.7
PAGE option
10 | there is a design issue in the | http://www.sciencetribes.com/postersetup.php |  |  | Go to the Information Service header bar,goto the |  |  |  | NO,need of invite and confirmation option
| ADD POSTER page option |  |  |  | POSTER option and then goto the ADD POSTER
| there is no confirmation |  |  |  | option , it can be seen in the screen shot slide no.10
and invite option
11 | there is a design issue in the | http://www.sciencetribes.com/documentfolder_details.php?crypt=Zm9sZGVyaWQ9Nw%3D%3D |  |  | In the Information Service header bar,go to the Document
| ADD FOLDER option at last |  |  |  | service,in that go to ADD DOCUMENT option,you can
| "confirmation"step |  |  |  | see it in the screen shot slide no.9 |  |  | FIXED
Date:09/08/2007
12 | the Article Search results are | http://www.sciencetribes.com/articlesearch.php |  |  | After getting the search results ,the Article Serach |  |  | FIXED
| not displayed in correct |  |  |  | Result is not in the correct format,it can be seen in
| format |  |  |  | screenshot slide no.1
13 | There is a design issue at |  |  |  | you can observe these design issues in the screenshot
| ADD POSTER,ADD FILE, |  |  |  | slide no.'s 2,3,4,6. |  |  | FIXED
ADD FORUM,GLOSSARY
pages
after deleting the request sent by colleagues,there is
14 | after deleting the member request |  |  |  | no specification of word "DELETED" u see it in |  |  | FIXED
| there is a coloumn over there |  |  |  | screen shot slide no. 5
when you go for INVITATIONS page,in that at the sent
15 | there is a need for correction | http://www.sciencetribes.com/invitation.php?crypt=bXNnPWQmc2VydmljZT1MSU5LUw%3D%3D |  |  | invitations it is unable to delete the request that is |  |  | FIXED
| such as "delete_success" |  |  |  | pending/rejected.
and also there is no change in
the status
[5 empty] | Here it is unable to chat 1-to-1 consistently,and also |  |  | FIXED
16 | the chat option is not working | CHAT MODULE |  |  | for "CONFERENCE" also
properly,sometimes it works
for 1-to-1,but it is not consistent
Date:10/08/2007
17 | Registration Form is not | http://www.abiteq.net/st/site/registration.php |  |  | In the URL specified ,it has to accept the Registration |  |  | FIXED
| working or no error message |  |  |  | form or else it has to display an error message.
is displayed
18 | "NEXT" button is not | http://www.sciencetribes.com/project_assignservices.php?crypt=c3VjPXkmcHJvamVjdGlkPTIzJmFkZHc9cw%3D%3D
| displayed |  |  |  | During ADD PROGECT module,there should be |  |  | FIXED
"NEXT" button,it cannot be displayed during the
2nd Step of the process.It can be seen in screen
shot slide no.1
19 | there is a Design issue and | http://www.sciencetribes.com/show_document.php?crypt=ZG9jaWQ9MTM%3D |  |  | After Accepting the Document Invitation and after |  |  | FIXED
| there is no Confirmation after |  |  |  | adding comment,it has to display a confirmation
| ADDing COMMENT. |  |  |  | regarding the COMMENT, and DESIGN should be
observed as shown in screen shot slide no.2.
20 | It should not display "From, | http://webserver:8080/invitation.php |  |  | When there are no Messages in Basic Service Invitations
| Subject,Received On" fields |  |  |  | the area should be "Blank",it should not display |  |  | FIXED
"From,Subject,Received On" fields as shown in slide
no.3 in screen shot.
21 | There is a Design issue,and | http://webserver/abiteq/billing/site/subscription_contact_info.php |  |  | When we enter the Zipcode & Phone no. It is
| it is not accepting the Zipcode |  |  |  | updating the Billing Information but not accepting |  |  | FIXED
| & Telephone no. | http://webserver/abiteq/billing/site/subscription_process.php?crypt=c2VydmljZWlkPTM3JnNlcnZpY2U9Rk9SVU1TJmludml0ZWlkPTM3MQ%3D%3D |  |  | the details .Even if we enter a US Phone no. it is
displaying the same two error's,and please check for
the Design issue and check for dictionary
"desc_subscription_contact_info" fields.
as shown in the slide no.4 in screen shot.
And there is also a need to check for a Dictionary
for the 2nd URL
22 | It is unable to Reject the | INVITATION MODULE |  |  | In the Invitation page,it is unable to reject the Premium |  |  | FIXED
| Invitation |  |  |  | User Membership even though if the user Rejects the
Invitation.
23 | Design issues and colon | http://www.abiteq.net/st/site/documentfolder_details.php?crypt=Zm9sZGVyaWQ9OA%3D%3D |  |  | Design and colon issues in slides 5,6,7
| issues . | http://www.abiteq.net/st/site/service_members.php?crypt=c2VydmljZWlkPTc5JnNlcnZpY2U9Rk9SVU1T | [5 empty] | FIXED
24 | crypting problem | http://www.sciencetribes.com/pass_recover.php?x26c36tz |  |  | There is need for crypting at the following link during the |  |  | FIXED
Forgotten Password Recovery which the client
gets to his mail.
Date:11/08/2007
[5 empty] | In the Documents & Posters,It is expected to show |  |  | FIXED
25 | When we EDIT the Folder, | POSTER'S AND DOCUMENTS MODULE |  |  | the changes made to the existing FOLDER,like if i
| the flow is repeating as ADD |  |  |  | would lke to make the SUB-Folder the next Main Folder
| FOLDER,and it is not making |  |  |  | it has to be accepted the changes,and also check for the
| the changes that are EDITED |  |  |  | PIPES that are shown after the INVITE Option as
| and also for PIPE SYMBOL |  |  |  | as shown in slides 1 , 2,5,6&9.
26 | In the SEARCH of Doc.& Folder
| of DOCUMENTS check for | In DOCUMENTS MODULE,SEARCH Option |  |  | When there are no SERACH results,it should display |  |  | FIXED
| dictionary the words repeating |  |  |  | No Results,and also when searching for both doc.and
folders it should display as Document Details as
shown in slides 3 & 4
27 | When Invitations are accepted |  |  |  | The accepted invitations are needed to bedisplayed in the |  |  | FIXED
| the accepted Documents are | DOCUMENT MODULE |  |  | Document list of Colleague ,by comparing the slides
| not displayed in the Document's |  |  |  | 6 & 7 it can be observed.
list of Collleague's list and
while Searching it displays
in the Search Results
28 | The Search Results are not | POSTER'S MODULE |  |  | Even though Folders are present in the My Posters |  |  | FIXED
| displayed |  |  |  | list, the Search cannot find and Display the list
of Folders in Search Results, by comparing the slides
8 & 9 it can be observed.
29 | Design issue in Forgott Pass | http://www.abiteq.net/st/site/index.php?msg=email_sent |  |  | When we CLICK on the Forgott Password, a window opens |  |  | FIXED
| word, crypt issue,and also |  |  |  | in that we obsreve the Design issue,and at the same
| Design issue in change password |  |  |  | window there is a crypt problem shown in URL,Design
issues are shown in slides 15 & 16
30 | There are Design , Colon | FILES MODULE
| Dictionary, Pipes,Extra Steps |  |  |  | These all issues can be obsreved as shown in slides |  |  | FIXED
| after Invite Option Issues in the |  |  |  | 10,11,12,13 &14
FILES Services
31 | New Colleague cannot be | http://webserver:8080/project_invite.php?crypt=cHJvamVjdGlkPTI2JmFkZHc9cw%3D%3D# |  |  | During ADD Project , in the Invitation Step an error |  |  | FIXED
| invited in the Project Module |  |  |  | message is displayed when we invite a new Colleague
for the project as shown in slide 17.
Date:14/08/2007
32 | Not forwarding to the next | http://www.abiteq.net/st/site/st&action=inc |  |  | There is an ERROR 404 displayed after sending an |  |  | FIXED
| page after sending an Invitation |  |  |  | Invitation During the process of ADDing the News
| while ADDing News. |  |  |  | in the NEWS Service module,but the invitation is
sent to the colleague.
33 | Invitations are Accepted but | http://www.abiteq.net/st/site/folders.php |  |  | When the Invitations of Folders are Accepted ,the |  |  | FIXED
| not Displayed,in POSTERS |  |  |  | colleagues list is not Displayed,to get displayed
| MODULE. |  |  |  | we are supposed to give a permissions to the
ADDed POSTER's.
34 | After ADDing the PROJECT
| there is a Fatal Error Displayed |  |  |  | After Accepting the Invitation of Project the Members
| in the Documents which were | In PROJECT MODULE |  |  | list should be Display the Status of the Project
| ADDed to the Project,even after |  |  |  | Invitation i.e.., Accepted/Rejected/Deleted. |  |  | FIXED
| Accepting the Invitation of the | http://www.abiteq.net/st/site/project_members.php?crypt=cHJvamVjdGlkPTIw |  |  | And it should Display the Documents list that are
| Project there is no Members |  |  |  | ADDED during the ADD PROJECT as shown in slide
| list Displayed. |  |  |  | no. 2 & 3.
35 | In the Document Module,After |  |  |  | At Confirmation step of ADDing the Document,only the |  |  | FIXED
| ADDing the Document at the | In DOCUMENT MODULE |  |  | Name of the Document that is Uploaded is to be
| Confirmation Step the Document |  |  |  | ADD Document is to be Displayed,as shown in slide
| that is Uploaded is not Displayed in |  |  |  | no. 1.
in correct format.
36 | In the Document Module,if we |  |  |  | When we select the ADD Document in the already
| select the ADD Document in |  |  |  | existing folder and fill the fields and in that if we click |  |  | FIXED
| the already existing Folder | http://www.abiteq.net/st/site/documentfoldersetup.php |  |  | ADD Folder,the link it direct the link to ADD Folder
| and fill the details and select |  |  |  | Module and it should follow all the steps,but it is directing
| the ADD Folder in that steps |  |  |  | the link to ADD Folder but following the EDIT Folder
| then it is directing to the EDIT |  |  |  | Module steps as shown in slide no. 4
Folder.
37 | While Editing the File,it's | http://www.abiteq.net/st/site/filesetup.php |  |  | When EDITing the file it is following the extra step |  |  | FIXED
| Process is following the |  |  |  | (confirmation step) which is not required while editing
| extra step(confimation step) |  |  |  | and after entering the fields it is supposed to go to the
| and it is also not forwarding |  |  |  | next page which is not directing as shown in slide 5
to the next page.
Date:16/08/2007
38 | During the ADD Document | ADD DOCUMENT MODULE |  |  | While checking for to and fro button's during the ADD |  |  | FIXED
| process at the Confirmation step |  |  |  | DOCUMENT process ,when clicking the prev button
| if we click the Prev Button |  |  |  | it should also display the Permission step and it is
| it is skiping the Permission step |  |  |  | again asking for Upload the fileas shown in slide 2
39 | In the Add Document Folder | ADD DOCUMENT MODULE |  |  | It should follow the INVITE and Confirmation steps, |  |  | FIXED
| if we select Add Folder in the |  |  |  | and it should not display the folder Unless it follows the
| Process it is not following the |  |  |  | INVITE & CONFIRMATION steps.with out clicking the
| INVITE & Confirmation steps | http://www.abiteq.net/st/site/documentfoldersetup.php |  |  | finish button the invitation is sent in this process.
| but the folder is added in the |  |  |  | as shown in slide 1.
Documents.
40 | When we check for members |  |  |  | In the Documents Module,if we check for Members of |  |  | FIXED
| list the ERROR is displayed |  |  |  | Folders then the ERROR message is displayed as
| in the URL Page | http://www.abiteq.net/st/site/documents_home.php |  |  | shown in slide 3
41 | The Invitations of Documents | INVITATION MODULE |  |  | The list of the Documents sent is to be Displayed |  |  | FIXED
| sent is not listed in the sent |  |  |  | in the sent Invitation list of INVITATION Module and
| Invitations,and the Folders list |  |  |  | the Folders list of FILES,POSTERS,ARTICLES,NEWS
| of FILES,POSTERS Invitations |  |  |  | Invitation are to be Displayed as shown in slide 5.
ARTICLES,NEWS are not Displayed.
42 | when clicking on the Show | PROJECT MODULE
| Profile an ERROR message |  |  |  | When we click on the SHOW PROFILE of Members |  |  | FIXED
| is Displayed in the Projects | http://www.abiteq.net/st/site/project_members.php?crypt=cHJvamVjdGlkPTE5 |  |  | of the Project some action/link is to be performed
| Module,in that by selecting |  |  |  | it should not display the ERROR messge as shown
| the Project and selecting the |  |  |  | in slide no.4
Members.
43 | In the FILES Module,if we | http://www.abiteq.net/st/site/filesetup.php?crypt=ZmZpZD00Ng%3D%3D |  |  | In the FILES Module, if we click on the Add File Option |  |  | FIXED
| click ok the Add File Option |  |  |  | of the Colleagues list the FILE must be Added into the
| in the colleagues list the file |  |  |  | Colleagues list, compare the slides 6 & 7..
is ADD into the MY FILES
venu 44 | In the ARTICLE Module ,when | http://www.abiteq.net/st/site/articles.php?crypt=YWN0aW9uPXBlcm1pc3Npb24%3D |  |  | It should Display Articles Permission Updated Successfully |  |  | FIXED
| we change the Permission then |  |  |  | in place of Articles_Permission_Updated as shown in
| Article_Permission_Update |  |  |  | slide no. 8
is Displayed
45 | After following all the steps |  |  |  | There should be a Proper link b/w the Invitet step & the |  |  | FIXED
| During the ADD Glossary,at | IN ADD GLOSSARY |  |  | Confirmation step of ADD Glossary Module,inspite of that
| the Confirmation step if we click |  |  |  | it is Displaying an ERROR Message as shown in slide 9.
| PREV button and enter the Invite |  |  |  | In SAFARI Browser
Page and again click the NEXT
Button an ERROR message is
Displayed.
46 | The SEARCH in the Glossary | http://www.abiteq.net/st/site/glossary_search.php |  |  | The SEARCH Result should Display only the Keywords |  |  | FIXED
| is showing all the TERMS that |  |  |  | that are typed in the Field,Inspite of that it is showing
| are ADDed in the Glossary | http://www.abiteq.net/st/site/glossary_terms.php?crypt=Zm9sZGVyaWQ9MjUmc2hvdz1hbGw%3D |  |  | all the Terns That are ADDed in the Glossary and
| Module, and there is Mismatch |  |  |  | There ias a Mismatch b/w the DATE Displaying as
| b/w DATE Displaying. |  |  |  | shown in slides 10 & 11.
47 | There is a Design issue at | http://www.abiteq.net/st/site/link_folderdetails.php?crypt=Zm9sZGVyaWQ9MTg%3D |  |  | It should follow the allignment correctly, as shown |  |  | FIXED
| the Confirmation step ADDing |  |  |  | in the slide no. 12
WEB Resources
48 | While ADDing the Folder in the |  |  |  | During the Process of ADDing the Folder in the Web |  |  | FIXED
| Web Resource Module at the | IN WEB RESOURCE MODULE |  |  | Resource at the Confirmation stepif we click the PREV
| Confirmation step, if u click the |  |  |  | button it is supposed to go to the Invite step,and it is
| PREV button it is jumping to |  |  |  | not supposed to send invitation again to any of the
| the Permission step and again |  |  |  | invited colleague.
it is sending the invitation with
link which is not ADDed to the
IE but it is not sending to FIREfox
49 | After accepting the Invitation | http://www.abiteq.net/st/site/links_folder.php?crypt=Zm9sZGVyaWQ9MTc%3D |  |  | After the Web Resource Invitation is accepted,at the |  |  | FIXED
| of Web Resource it is not |  |  |  | Permission level it is supposed to confirm for the
| checking for Permissions |  |  |  | Add Link With Approval Permission (Web 2) During
the ADDing Link whether to ACCEPT/REJECT which
is equal to the Add Link Without Permission(Web 1)
Folder of Web Resources by comparing slides 13 & 14
50 | There is a Design issue in | http://www.abiteq.net/st/site/blog_details.php?crypt=YmxvZ2lkPTc5 |  |  | At the Confirmation step of ADD Blog Module the |  |  | FIXED
| the Confirmation step During |  |  |  | allignment should be corrected and also when we click
| the ADD Blog Process and also |  |  |  | the PREV button at the Invite step it is supposed to
| if we click PREV button at the |  |  |  | go to the Permission step, for both issues see slides
| Invite step it is not directing to |  |  |  | 15 & 16.
the Permission step an ERROR
is displayed.
51 | While EDITing the Folder in the |  |  |  | When we EDIT the Folder in the BLOGS Module,it |  |  | FIXED
| BLOGS Module, the ADD | IN BLOGS MODULE |  |  | is supposed to EDIT the Folder not ADDing the Folder
| Folder Process is followed. |  |  |  | again.
not fixed52 | In the Message Module,the | http://www.abiteq.net/st/site/compose.php |  |  | When the Message is sent , then the message to be
| Message is sent ,but it displays |  |  |  | displayed is ' message sent successfully',inspite of that
| an ERROR on the page in the |  |  |  | an ERROR message is displayed as shown in slide 17
| safari browser v 3.0.2(522.13.1) |  |  |  | and also check for Defaulty settings as TO:156
| and also using that browser |  |  |  | during the reply of a message as shown in slide 18
| if we click reply and send |  |  |  | in the safari browser.
the message, then the message
is sent succesfully in it while
while replying there is a default
setting TO:156.
Date:17/08/2007
FIXED
53 | When we click the SEARCH | http://www.abiteq.net/st/site/msg_search.php |  |  | When there is no Messages regarding the subject
| the 'No Records Found' message |  |  |  | or Message then the SEARCH Result should display
| is displayed. |  |  |  | No Records Found' message as shown in slide 1
54 | colon missing and Repetation | http://www.abiteq.net/st/site/actionlistsetup.php |  |  | ADD Action Page need to be in correct format as |  |  | FIXED
| of word 'Date'at Startdate Date |  |  |  | shown in slide 2
venu 55 | when we click on the Archive, | http://www.abiteq.net/st/site/eventDetails.php?crypt=ZXZlbnQ9NTU%3D |  |  | When we click on the Archive button in the EVENTS |  |  | FIXED
| in the EVENTS Module then an |  |  |  | Module then the EVENT should be Archived.the message
| ERROR 'Service Not Available' |  |  |  | should not be displayed as shown in slide 5,
| is dis[played.and also if we |  |  |  | and also if we click on Remove button it is unable to
| click remove it is unable to remove |  |  |  | remove the EVENT.
not fixed56 | check for the Dictionary for | http://www.abiteq.net/st/billing/site/subscription_process.php |  |  | the display should be in correct formatnot as shown
| the URL specified, the message |  |  |  | in slide no 4
desc_subscription_process
57 | When the Glossary is made | http://www.abiteq.net/st/site/glossary.php |  |  | When the Glossary is made Inactive then there should |  |  | FIXED
| Inactive then there should be |  |  |  | be no Permissions and Set Price options.
no permisssions and set Price
options.
venu 58 | The site is not accepting the | http://www.abiteq.net/st/site/index.php |  |  | The user Registration is accepted but during log in |  |  | FIXED
| log in, for the Organization |  |  |  | it is unable to accept the user,and when we click on the
| Registration Module. |  |  |  | Forgott Password the user gets the password to his
mail, as shown in slides 6 & 7.
59 | In the ADD Document Module | http://www.abiteq.net/st/site/documentsetup.php |  |  | During the Add Document Module,after uploading the |  |  | FIXED
| while adding document,if we upload |  |  |  | document and click NEXT and move to on and again
| the file and move to next step and |  |  |  | come for the 1st step it is not supposed to ask to
| then click PREV step then it is |  |  |  | upload the document again and also check for the
| again asking for upload of file. |  |  |  | Design issue as shown in slide 9.
and there is a Design issue at the
confirmation step.
60 | In the Internet Explorer the there | IN LOG-IN PAGE |  |  | There is a Design issue to be clarified as shown in |  |  | FIXED
| is a design issue. |  |  |  | slide 8
not fixed 61 | In the FILES Module,if we | FILES MODULE |  |  | It is supposed to display the File when we Upload the
| click on the Add File Option |  |  |  | File During the ADD File option in the colleagues list.
| in the colleagues list the file |  |  |  | in the colleagues/Owner's list.
is not displayed even after the
file is uploaded.
62 | In the ADD Webbrowser | http://www.abiteq.net/st/site/link_creation.php |  |  | It is supposed to direct to any of the page when the |  |  | FIXED
| module if we click on the Cancel |  |  |  | Cancel button is clicked and also check for Colon
| button the Cancel action is not |  |  |  | and Allignment's missing as shown in slide 10.
directing to any of the page,and
also check for the Colon and
Allignment issues.
Date:18/08/02007
not fixed 63 | In Web Resource Module,if we | http://www.abiteq.net/st/site/link_search.php |  |  | When we Search for any of the links in the Colleague's |  |  | FIXED need to work on colleagues link's
| Search for any other link in the |  |  |  | list of Web Resources module, it should Display the
| Colleague's list it is Displaying |  |  |  | links which are present in the colleague's list which is
| No Records Found' and also check |  |  |  | not shown it can be observed in slide 1, and also
| for Design issues,colon issues. |  |  |  | maintain the DESIGN,Colon issues as shown in
slides 2,3.
64 | In the Web Resource Module of | IN WEBRESOURCE MODULE |  |  | When we set the Permission as 'Add Link with Approval' |  |  | FIXED
| Colleague's list it is not checking |  |  |  | then it is supposed to ask the confirmation after Adding
| for Permission's, and there is | http://www.abiteq.net/st/site/links_home.php |  |  | the link's which is not happening it is shown in slides 4 & 5
| no ARCHIVE option. |  |  |  | an ARCHIVE option should be placed at the options
as shown in slide no 6
65 | There's no Differentiation b/w the | http://www.abiteq.net/st/site/invitation.php |  |  | As there is a Differentiation b/w the Foldes and File |  |  | FIXED
| Folders and the Documents, | INVITATION MODULE |  |  | as shown in slide 9, the same Differentiation is required B/W the
| Links,Posters in Sent Invitations. |  |  |  | Folders and Documents,Posters,Links Modules in the Sent Invitations
as shown in slide 8 & 10
66 | There is no ARCHIVE Option in | IN EVENTS MODULE |  |  | When there is an ARCHIVE Option in the EVENT Module |  |  | FIXED
| the EVENTs Module when we click |  |  |  | the Option should be displayed at the EVENT details
| on the Event but it is displaying the |  |  |  | which is not displayed as it Displayed for the Phone
| the Archive option when we click |  |  |  | Conference Event.
on the Phone Conference event.
67 | check for the Design,Colon, | IN ACTION LIST,GROUPS MODULES |  |  | check for slides 7,11,12 |  |  | FIXED
Allignment,Dictionary issues
Date:20/08/2007
68 | In the Conference Module,when | http://www.abiteq.net/st/site/conference_schedule.php |  |  | In the Conference Module,after filing the Profile Details |  |  | FIXED
| we click Next button it is not |  |  |  | when Scheduling the Meeting the while clicking Next
| forwarding to the next page,and |  |  |  | button it is supposed to go for next page and also check
| also check for Dictionary. |  |  |  | for dictionary as shown in slide 1
69 | There are repetation of Phone, |  |  |  | When we go through this path MyAccounts ->Preferences |  |  | FIXED
| Subscription,Document Folder | In MY ACCOUNTS ->Preferences Module. |  |  | and click on the Enable/Disable link in that page
| Modules while enable/disable |  |  |  | there we can find the all Modules, and if we Disable the
| the Modules. |  |  |  | Subscriptions Module then also the Module is Enabled.
as shown in slide 4
not fixed 70 | There is a need to check for | In Blog Service, Add Blog Module |  |  | It is supposed to maintain the Design at the Confirmation
| Design issue in the Blogs |  |  |  | step During the Add Blog Module, as shown in slide 2
Module.
71 | Check for Design issue and | http://www.abiteq.net/st/site/actionlist.php |  |  | There should be no Fatal Error to be displayed,and |  |  | FIXED
| Fatal Error is Displayed in the |  |  |  | check for the Design, it has totally changed the Design
| Action list. |  |  |  | if the page, as shown in slide no.3.
72 | There is a difference b/w display | http://www.abiteq.net/st/site/permissions.php |  |  | In any of the Browser's i.e.., IE and Mozilla FireFox |  |  | FIXED
| of Permissions in IE and MOZILLA |  |  |  | the display of Permissions Module is supposed to be
| FIREFOX Browsers,and only the |  |  |  | same,which is not happening as shown in slides 5,6
| files created are displayed no |  |  |  | All the Permissions need to be displayed.
Folder permission is displayed.
73 | If we change the Permission | IN PERMISSION MODULE |  |  | When we change the Permission of any Service then there |  |  | Colleague Permission levels will not change
| of Forum or any of the service |  |  |  | should occur Relevant changes in the Permission level
| there is no change in the |  |  |  | of Colleagues list which is not happening.
Permission level's when we check
for the colleagues Permission
Date:21/08/2007
not fixed 74 | when we click on the email link | https://www.billing.abiteq.com/process.php |  |  | when we click on email link of in the URL page it is
| page in the URL it is not directing |  |  |  | supposed to direct to any of the page which is not
| to any page. |  |  |  | happening as shown in slide 1
75 | The chat module is not working | CHAT MODULE |  |  | It is supposed to work Chatting in every Browser,which |  |  | FIXED
| in the IE and SAFARI Browsers. |  |  |  | is not working in the IE and SAFARI Browser's, these
Browsers are getting the invitation to chat, but after
accepting it is not showing the chat window.
not fixed 76 | The Phone VOIP Module is uable | IN PHONE VOIP MODULE |  |  | It is supposed to access Phone VOIP Module During the
| to get accessed during the TRAIL |  |  |  | Trail Period offer of Premium Membership .
Period of Premium Membership
offer
not fixed 77 | During the Premium member user | IN PHONE VOIP MODULE |  |  | It is supposed to follow all the steps during the Premium
| the 'Contact Information" step is |  |  |  | membership,if the 'contact Information' is not necessary
| missed and if it is not required |  |  |  | then it should not display while selecting the Trail Period
| during the Trail Period offer then it |  |  |  | offer as shown in slides 4 & 5, Dictionary check for slides 2 & 3.
it should not be displayed and also
check for Dictionary.
not fixed 78 | In Phone VOIP after accepting the | IN PHONE VOIP MODULE(Advanced User) |  |  | In Phone VOIP Module if the Invitation is accepted then
| Invitation it is unable to display the |  |  |  | it is supposed to Display in the Colleague's list,and
| Colleagues list and also after accepting |  |  |  | it is not supposed to send the Invitation again .
the Invitation once the user is getting
the Invitation again for Advanced Users
79 | In the MY ACCOUNT Services, in | IN MY ACOUNT ->PROFILE MODULE |  |  | When we Edit the Profile and click on SAVE then the |  |  | FIXED
| Profile Module while EDITing the |  |  |  | page is supposed to SAVE the edited Profile and should
| Profile the SAVE and CANCEL Buttons are |  |  |  | direct to the respective page.
replaced with PREV,NEXT,SKIP NOW
buttons
80 | Check for the dictionary in the | IN CONFERENCE MODULE |  |  | The Dictionary words are supposed to be corrected |  |  | FIXED
| Conference Module |  |  |  | which is not done as shown in slides 6 & 7
81 | There is a Display problem in the | IN PERMISSION MODULE |  |  | When we click the Change Permission Option ,then the |  |  | FIXED
| Permission Module,when we click |  |  |  | Set Permission is opened for the respective module
| on the Change Permission then the |  |  |  | only,as shown in slide 13
set Permission is opened for another
module
not fixed 82 | In Permission Module ,there is a | IN PERMISSION MODULE |  |  | It is supposed to display only the Permitted Services
| display problem. |  |  |  | to the Collleagues which is not happening as shown
in slides 8,9,10,11,12
83 | In Glossary Module,there is no | IN GLOSSARY MODULE |  |  | It is supposed to display the Permission's for the |  |  | FIXED
| display for the Permission's in the |  |  |  | Glossary Module in the Colleague's list, which is not
| Colleague's list |  |  |  | happened as shown in slide 14.
not fixed 84 | In Sent Invitation Module, in each | IN INVITATION MODULE |  |  | It is supposed to be in correct format,whch is not happene
| Module there is a Format Issue |  |  |  | as shown in slide 15
Date:22/08/2007
not fixed 85 | when we click the 'submit' button | https://www.billing.abiteq.com/subscription_mem_billing.php |  |  | After accepting the Invitation of the Project,in the process
| in the billing Module it is not directing |  |  |  | of Subscription the 'Submit' button is not working and
| to any page |  |  |  | also check for validations,Dictionary and Display issues
as shown in slides 2,3,4
86 | check for the Design issue and | IN PROJECT ->EDIT PROJECT MODULE |  |  | There should be correction of design and colon issues |  |  | FIXED
| Colon issue in the Edit Project |  |  |  | as shown in slide 1
Module
87 | The Chat Module is not working in | CHAT MODULE |  |  | In the Safari Browser,even though the Invitation for |  |  | FIXED
| SAFARI Browser |  |  |  | Chat is accepted but the Chat Window is not Displayed.
not fixed 88 | In the Event Module the Phone | IN EVENT MODULE |  |  | It is supposed to Remove from the Event list when the
| Conference event is Archieved but |  |  |  | Phone Conference Event is Archieved and it is not supposed
| the Phone Conference Event is not |  |  |  | display in both the Archives list as well as Event list.
Archieved on that certain date.
89 | the Reject option is not working in | Web Resource Module |  |  | When a User ADD's a Link to the Colleagues list then |  |  | FIXED
| Web Resources module |  |  |  | the colleague has to Approve/Reject his Link,If the colleague
Approve's the Link then then it is added and when he Rejects
it is supposed to Remove the Link from the colleagues list
90 | There is Repetation of Subscription, | In MY ACCOUNT ->PREFERENCE |  |  | When there is Subscription Module then it is not |  |  | FIXED
| Phone Modules in the Enable/Disable |  |  |  | supposed to repeat Subscription,Phone Modules .
| Services. |  |  |  | as shown in slide 7
91 | In Forum Topic ,if we click on the | http://www.sciencetribes.com/PAGE_FORUM_ADD_TOPIC&topicid=66 |  |  | In the FORUM module if we click at the Forum topic's |  |  | FIXED
| Edit buttton the page is directing to |  |  |  | Edit Button the page has to direct to the Edit Forum
| the ERROR page |  |  |  | Topic Page which is not happened it is directing to the
Error Page as shown in slide 11.
not fixed 92 | there are Design issues and colon | PLZ check the slides 5,6,8,9,10,12 |  |  | It is supposed in the correct DESIGN in all the Modules
issues .
93 | During the process of Adding the | IN WEB RESOURCES MODULE, ADD BLOG |  |  | It is not supposed to send the Invitation again in the |  |  | FIXED
| Folder in WEB Resources,at the | MODULE |  |  | Wizard's which is happening in the safari browser.
Confirmation step if we click the
PREV button and then click NEXT
button in the Invite step the Invitation is
again sent to the user of SAFARI
Browser user version3.0.2(522.13.1)
Date:24/08/2007
94 | In Add Poster,after Uploading the | IN ADD POSTER MODULE |  |  | During the process of Add Poster,at the Custom html
| Photo in the Custome Html Editor |  |  |  | editor after Uploading the Photo it is supposed to be
| step it is Redirecting to the Previous |  |  |  | in the same page Until and unless you click on the
| step i.e.., (Select a Template) |  |  |  | NEXT button.
95 | During the Process of Add Folder, | IN ADD POSTER MODULE |  |  | At the Confirmation step if we click on the PREV
| at the Confirmation step if we click the |  |  |  | button then it has to go back each and every step that
| PREV button it is going back correctly |  |  |  | we followed during ADD Poster Process, and also
| upto the Custome html editor and at |  |  |  | correction of Date Format at the Read Date as shown
| that step if we click PREV button then |  |  |  | in slide 1.
| it is jumping to the First step, and | http://www.sciencetribes.com/show.php?crypt=Zm9sZGVyaWQ9MzkmcG9zaWQ9NzI%3D
also check for Date format at the
URL specified .
96 | Check for the Permissions in the | IN ADD POSTER ------->PERMISSION MODULE |  |  | When the Permission is set to Commentwith Approval
| Posters Module, if Give Permission |  |  |  | then the owner has to get the Request regarding the
| as Comment with Approval then the |  |  |  | Comment which is not happening.
Colleague post the comment it is not
at all Displaying the Comment and
not asking for the Approval Permission
97 | Archive option is not working, when | IN WEB RESOURCE MODULE |  |  | In Web Resource if we click on the ARCHIVE option
| clicked on the Archive,it is unable to archive |  |  |  | it is supposed to Archive the link which is not happened.
| the link and Displaying the Error msg |  |  |  | and it is displaying an error message.,and also the same
| There's problem in performing this task' |  |  |  | problem is same with the Folder's ,here the folder is
| and also check for the Folder option, |  |  |  | archived but the folder is not supposed to be in the list.
it is archived but it is not removed from the
list.
98 | In forum's is it possible to Archive | IN FORUM MODULE |  |  | There is no need for,Archive option for the already
| the already Archieved Forum. |  |  |  | Archived Forum,plz compare slides 4 & 5.
99 | While Adding Folder in the Files | IN FILES------>ADD FOLDER MODULE |  |  | It is supposed to go for the Previous step if we clcik
| Module,at the Confirmation step if we |  |  |  | the PREV & NEXT button and when we ADD File/Folder
| click on the PREV button,and when we |  |  |  | in another Browser and send Invitations
| again click on the PREV it is unable to |  |  |  | and click on the PREV and click on NEXT button
| redirect to the Permission step in SAFARI |  |  |  | then the Invitation is sent again to SAFARI Browser.
Browser and if we add file/folder in another Browser that
process if we click the NEXT and PREV
buttons the SAFARI browser gets the
Invitations again and again
100 | check for the Design issues and | plz check the slides 2,3,6,7,8 |  |  | it is supposed to be in the correct allignment
colon issues.
Date:27/08/2007
101 | The log-in's and the registration is not | Registration Module |  |  | It is supposed to accept all the log-in's which are already |  |  | FIXED
| working for already registered mail-id's |  |  |  | registered ,and it should accept all the mail-id's that
| and it is accepting only the gmail account's |  |  |  | are used for the registration.
it is not accepting any other mail-id's
102 | In the safari Browser it is unable to | FILEs MODULE |  |  | It is supposed to direct to the next step while ADDing
| ADD File ,during Adding File when we |  |  |  | File which is not supporting in the SAFARI browser.
click on the next button it is not directing
to next step.
Date:28/08/2007
103 | During Add Project the Confirmation | IN ADD PROJECT MODULE |  |  | While Adding Project it supposed to follow all the steps
| step is not followed |  |  |  | (i.e..,Title ,Assign Services,Invite & Confirmation )
which is not happened it is Adding the Project without
following the Confirmation step.
104 | For the Folder in the Files Module there | IN FILES MODULES |  |  | It is supposed to have Deactivate,Archive options
| is no Deactivate , Archive options |  |  |  | for the Folders in the Files Modules.
105 | The permission updates are sent to the | Updates Invitations sent to mail-id |  |  | when the log-ins are not working then it is supposed
| mail-id when it is not accepting |  |  |  | not sent the updated invitations also to the mail-ids
| the log-in's in ST site, it is not supposed |  |  |  | for which log-ins are not accepted as shown in slide 1.
to send the updates also
106 | No comment is not posted in the Posters |  |  |  | In Posters Module, after accepting the invitation which
| Module, which is having the permission | In POSTERS MODULE |  |  | is possessing the permission comment with approval
| comment with approval which is not asking |  |  |  | if the colleague posts a comment it is supposed to get
| for any approval permission. |  |  |  | approval for the comment which is not happening
107 | It should not display the Archived posters |  |  |  | When clicked on Archive ,the Poster is archived but
| in the Home page of Poster services | IN POSTERS MOODULE |  |  | it is still seen in the Poster's Home Page which is not
supposed to be displayed
108 | check for the Dictionary in the forum's | Forum Module |  |  | plz check the slide 2
Subscription Module
Date:29/08/2007
109 | In Edit File,after uploading file in 1st step | IN FILES MODULE |  |  | It is supposed to maintain the Same steps while Edit
| it is displaying correctly but when clicked |  |  |  | File which is not happening as shown in slides 1 & 2.
Next' it is displaying the process done for
Add file.But without making any changes
if we click Next then the display is shown
correctly.
Date:01/09/2007
110 | while Adding the Folder,Displaying the | FORUM ->ADD FOLDER |  |  | It is supposed to follow all the steps without any link
| Error message 'Service Not Available' |  |  |  | broken,and also while Adding Folder the add folder
| and also while adding folder Add Folder |  |  |  | should be highlited.
is not highlited.
111 | there is no archive option for the folders | FORUM MODULE |  |  | It is supposed to have Archive option for Folder of Forum.
112 | Display of DATE should be Relevant to the | ALL MOST IN EVERY MODULE |  |  | It is supposed to display the DATE in the format which
| DATE format set in the Preference of |  |  |  | user sets in the Preferences module of My Account.
My Account module.
113 | In colleagues list,with 'post &comment with | BLOGS ->Post Blogs |  |  | In the Blogs,if the colleague is having the 'Post & comment
| approval'permission it is not displaying the |  |  |  | with approval' permision then it is supposed to display
| posts that are waiting for approval in the |  |  |  | the Posts that are waiting for Approval in the respective
| owners list. |  |  |  | blog owner's list.
114